## Sheet1
Week commencing	Plan
29 October 2012	Research mapping system, basic implementation
05 November 2012	Build location class … automated GPS and network location
12 November 2012	Read about PUSH/PULL communications as well as security concerns and other related topics.
19 November 2012	Continued reading about android implementations of PUSH/PULL, quick implementation of both with conclusion on which to use.
26 November 2012	Server technology selection and implementation of basic service. Receive users location data and return any other users data within an area. User authentication of some sort
03 December 2012	Final Android implementation of chosen technology. Built alongside server development
10 December 2012	Gather a handful of testers and spread out. Tweaking and bug fixes.	Term finishes 15th
17 December 2012	Re-factoring of all code and any fixes or small trivial additions
24 December 2012	//
31 December 2012	//
07 January 2013	Decisions on how to track and move units. Implementation of structures and units.	Term starts 7th / Revision week
14 January 2013